Access to Scholarly Content: Gaps and Barriers

1. Project definition

  - Sponsors

The project sponsors are the Research Information Network (RIN), the Joint Information Systems Committee (JISC) and the Publishing Research Consortium (PRC). A wider group of organisations, listed in Annex 1, actively support this project.

1.2 Aim

The aim of the project is to investigate and quantify the extent to which members of different communities in the UK can gain ready access to formally-published scholarly literature, in particular journal articles and conference proceedings; and to identify priorities in filling gaps and overcoming barriers to access, and actions that might be taken to that end. This is envisaged as a practical project, designed to identify some of the ‘quick wins’ actions which could provide better access to information resources for members of various communities in the UK. It complements other projects being commissioned by the sponsor group; these consider the longer-term future of scholarly communications.

1.3 Objectives

The objectives of this project are

- to conceptualise and map, on the basis of definitions agreed with the project sponsors, the nature and extent of the gaps in and barriers to access to scholarly journal articles and conference proceedings, as experienced by members of different communities in the UK, in academia and beyond;

- to quantify, as appropriate and feasible, access gaps and barriers for different communities;

- to provide an evidenced assessment of the significance of those gaps and barriers for different communities, in the light of their information requirements (which may extend beyond journal articles and conference proceedings) and levels of demand, their behaviours, and their working practices;

- based on this, to identify priorities in seeking to reduce or eliminate those gaps and barriers, and to review the actions that might be taken to that end; and

- to produce an agreed set of criteria for prioritising actions, and a prioritised action plan which sets out the costs for each action.

1.4. Background and key issues

Access conceptualised

1.4.1. Access refers to a person’s or a machine’s ability easily to discover, read, and use a paper in which they might be interested, and in particular an ability to do all that in relation to the published version of record. Access in this sense may be taken as implying that the person or machine can do some or all of the following: read, print, download, store, manipulate, or disseminate. To put the last three in context, it is recognised that with the advent of new technologies, some may wish to extend their use of accessed material to store, manipulate and disseminate to enhance their research. The project should therefore also establish where and the extent to which this is a requirement and determine the nature of any barriers that restrict this type of use.

- the basic metadata (author, title, place and date of publication and so on) or the full metadata relating to the paper;

- an abstract describing the content of the paper;

- the full text of the paper.

It is important to state that researchers’ interest in these different levels of accessibility will depend upon how they want to use the information that they are accessing. Something which one group would consider an insufficient level of accessibility may be perfectly adequate for another group. As far as this research project goes, access should be seen as a product of the user’s needs, rather than a universally-defined concept.

1.4.2. There is a sense in which published scholarly content is, as it always has been, accessible to anyone who has the financial means to purchase it, along with the equipment (technical and intellectual) to read and make use of it.

1.4.3. In practice, however, and in particular as the volume of literature has expanded, the primary means of access is through membership of one or more institutions that has the resources to purchase content (or, now, licences for access to content) on its members’ behalf; or through a public or national library that has been able similarly to purchase it. For practical purposes, therefore, access currently depends largely on institutional and other libraries, and the range and extent of the content they can provide to their members and users. Once again, however, we recognise that there are other ways for researchers to access research information, and in practice how this access is secured may differ between constituencies.

What are the barriers and gaps in access and who experiences them?

1.4.4. Since published content is in principle available to anyone with the necessary financial means and equipment, access gaps must be conceptualised and defined in tandem with the various kinds of barriers to access.  ~Examples of barriers that persons or machines may encounter to the different kinds of content outlined above may include the following, and there will be others that the project will identify:

- lack of awareness of the resources that are available to them

- lack of access to appropriate hardware

- lack of access to appropriate software

- content in a format which is not suited to the needs of the researcher

- lack of membership of a library that has purchased a licence

- a requirement to make a payment for access to the desired content at a level which the user considers disproportionate to the anticipated benefit

- a burdensome purchasing process

- conflict between the author’s or publisher’s rights and the desired use of the content

- digital rights management or technical protection technologies that prevent the desired use of the content.

1.4.5. The range of content to which members of higher education and related research institutions in the UK have ready access– along with how they can gain access and the uses to which they can put content - has increased significantly over the past decade, as a result both of the digital revolution and of the ‘big deal’. No institution or library provides full and immediate access free at the point of use to the full text of the contents of all the scholarly journals published worldwide, even those produced in English, but this is rarely necessary since most institutions do not cover every academic field. Nonetheless, there continue to be some gaps in access free at the point of use for members of the higher education and research communities in the UK, for one or more of the reasons outlined above. What is important is whether researchers experience these gaps as a problem or not. If they are a problem, various measures may be adopted to overcome these gaps and barriers, with varying levels of cost, difficulty or success, particularly in relation to access to the published version of record.

1.4.6. People who are not members of a university or research institution but work in industry or in the public and voluntary sectors are likely – along with members of the general public - to encounter many more difficulties in seeking access to journal articles or similar publications. Again, they may adopt various strategies in seeking to overcome such difficulties: the research should identify these strategies.

1.5. Scope

1.5.1. The strong focus of this study is on access, as defined above, to journal articles and conference proceedings. It may be desirable, however, in pursuance of objective 1.3.iii above, to consider existing information on other research outputs such as monographs, books, dissertations, research data, supplementary data (that which is made available as supplement to the Version or Record), research algorithms and software as well as broader information needs, e.g. economics data, news, patent information, historical public records, etc, to enable an analysis of relative importance of different information types (which may vary for different constituencies)It would also be helpful to set the importance of information needs broadly in the context of other priorities and needs of different constituencies.

1.5.2. The focus of the study is similarly on the UK, but the contractor may wish to draw for comparative purposes on readily-available information about access gaps and barriers in other countries. The contractor will not be expected to undertake primary research outside the UK

1.5.3. The study should seek to map the experience of access – and of gaps and barriers, and of how they might be overcome - for relevant socio-economic or occupational groups in the UK, for those living in different parts of the UK, and for those interested in the scholarly literature in different subject or disciplinary areas. Such groups may include the health service, government, research institutions, industry – both large and small and medium enterprises – and the voluntary and community sector. The project sponsors are happy to consider other user groups suggested by the contractor. The differing information requirements and levels of demand, behaviours and working practices of various groups should inform the assessment of gaps and barriers.

1.6 Related Work

1.6.1. This project is one of four projects being taken forward by the group of organisations listed in Annex 1.  The others are on:

      - transitions to e-only publication

      - dynamics of improving access to research papers

      - futures for scholarly communications (horizon-scanning)

1.6.2. The scope of each of these projects is in part defined with reference to the others.  While the projects are reasonably distinct, there is a degree of overlap, which will need to be managed. It is expected that the findings from this study will be an important input to project ii. on the dynamics of improving access.

1.6.3. Although a full and detailed assessment of access gaps in the UK has not been produced as yet, a number of reports relevant to this study have been produced by the RIN, JISC, the Publishing Research Consortium and others in the UK, along with studies of experience in the US and Europe. The study should draw on this work as appropriate.

1.7. Resources

Up to £60,000, including expenses but excluding VAT, will be available for this project.

Additional resources can also be made available by the project sponsors.

Technical resources for survey work, including online questionnaire design, scripting, piloting and fielding of the survey, analysis of data and creation of required data tables and charts.

Email contacts for survey work:  email lists of authors sampled randomly from those who have published in more than 15,000 journals (includes researchers in academia, hospitals and medical schools, industry, government and other research institutes); individuals in industry who subscribe to specialist scientific magazines; individuals who have registered to purchase single articles.

Tenders should provide two sets of cost estimates, one which includes the provision of these resources (free of charge) and one where these resources are not provided.

1.8. Dates and milestones

The project is to start in mid-April 2010.  The final outputs from the project are due in October 2010.

2. Project processes and outputs

2.1. The project is to be undertaken in a highly collaborative way, involving all the key constituencies throughout.  The organisations noted in Annex 1 have agreed actively to support this project and to act as a reference group whose terms of reference will include to provide such information as the project might need (within constraints), to offer timely and high quality feedback to the project, to help validate its findings, and to encourage their members or partners (as appropriate) to do likewise.

2.2. Oversight

The project sponsors form a subset of those organisations noted in Annex 1, and they have agreed to form a steering group for the project, whose terms of reference include oversight and guidance, providing advice to the contractor and reviewing work in progress at appropriate stages of the project.  The chairmanship and modus operandi of the panel (e.g. whether it confers virtually or meets face-to-face) and the frequency of interaction with it will be determined on project start-up.

### 2.3 Methodology

The contractor will propose and justify a robust methodology for addressing the objectives and scope of the project. The sponsors are not prescriptive about the chosen methodology but envisage the need for:

- A literature review to establish the current state of knowledge and estimate broad parameters against which the outcomes can be compared

- A survey amongst broad and representative groups of users that establishes and quantifies for them levels of access, gaps and barriers, in the light of their various information requirements.

- Interviews with a range of users to provide more qualitative depth to survey results

The expert panel should be consulted about the detailed elaboration and implementation of the methodology.

### 2.4 Outputs

2.4.1. The outputs from this study are expected to be a report detailing the findings that address the objectives set at 1.3 above.  It is envisaged that this may take the form of a short summary highlighting the main quantitative and qualitative findings and a more detailed document that will provide sufficient granularity of data for use in subsequent modelling. The report should include recommendations and a costed action plan. As well as considering the gaps, barriers and priorities for each user group, the report should consider similarities and crossover between the needs of the various groups.

2.4.2. The report will be published in the name of the sponsors with due acknowledgement to the contractor.  Upon completion of the project, copyright will be assigned to the sponsors for the report, which will be issued under a Creative Commons ‘attribution’ licence. The sponsors will expect as much of the primary data as possible to be made publicly available and will seek arrangements with the contractor to enable this.

### 2.5 Monitoring and progress reporting

The project will conform to the contractor’s plan, agreed at the outset with the sponsors. Any deviation from the plan will need to be cleared with the sponsors.

In addition to the interface with the expert panel, as described above, the contractor will be expected to provide, within reason, regular email or phone feedback to the sponsors as the project progresses. For this purpose, the sponsors will assign a project manager who will oversee progress and liaise with the contractor.

3. General information

### 3.1 About the project sponsors

The RIN (www.rin.ac.uk) was established in 2005 and is funded by a consortium of the four higher education funding bodies, the three UK national libraries and the seven research councils. Its mission is to develop the evidence base, provide guidance and advice and promote change in matters relating to the provision of research information in the UK.

The JISC (www.jisc.ac.uk) supports higher and further education by providing strategic guidance, advice and opportunities to use information and communications technology to support research, teaching, learning and administration.

The PRC (www.publishingresearch.net) is a group of associations and publishers, which supports global research into scholarly communication in order to enable evidence-based discussion. Its objective is to support work that is scientific and pro-scholarship. Overall, it aims to promote an understanding of the role of publishing and its impact on research and teaching.

### 3.2 Procurement

The RIN is hosted by the British Library at its London site in St Pancras. As such, the RIN makes use of British Library procurement procedures. Contractors will therefore be expected to conform to the RIN’s terms and conditions, which are modelled on those of the Library, and, at the outset, to register with its e-Tendering Service in order to be able to submit tenders – see http://www.bl.bravosolution.com/web/login.shtml. During the formal tendering period, prospective contractors will receive guidance from the British Library’s Contracting and Purchasing Unit.

### 3.3 Tendering

In responding to the invitation to tender, prospective contractors will explain how they would meet the objectives and achieve the outputs set out in this specification. The sponsors encourage ideas, views and judgement about how best to address and take forward the issues covered by the specification. On that basis, prospective contractors should submit a proposal addressing the following, which will act as evaluation criteria for bids:

- a clear understanding of the purpose of the project, the role it will play in the ongoing development of policy and practice in this area, and hence the appropriate shape and quality of the project outputs, recognising this role.

- a full understanding of the project specification, its rationale, objectives, scope, risks and issues.

- an appropriate and justified methodology that commands the confidence of the project sponsors, and includes a convincing strategy for identifying and managing risks.

- a sampling plan for surveying the experiences of different communities in the UK, indicating where samples will be drawn from and how many to meet the requirements of the study.

- a clear and feasible work plan, including a Gantt chart (or similar) and project management arrangements.

- a financial statement indicating a breakdown of costs (including details of who will work on the project for how many days) and demonstrating value for money.  This should include a breakdown of the full costs of carrying out a survey and analysis, including sample provision, with and without the sponsor-supplied resources outlined in section 1.7. (Details of contact persons to discuss these resources will be provided upon request).

- a team that can demonstrate an ability to undertake this project, to include a track record of quality work in this area, methodological expertise, and project management capability.

The total length of the proposal document should be no longer than 8,000 – 10,000 words including figures and figure legends, charts, footnotes and references.

The sponsors will shortlist prospective contractors and may invite them to attend a meeting to present their proposals.

Annex 1 - Transitions in Scholarly Communications

The scholarly communications landscape has been transformed over the past few years, in the UK and across the world. Technological change has brought – and continues to bring – profound changes in the roles that  researchers, funders, research institutions, publishers, aggregators, libraries and other intermediaries play in disseminating and providing access to quality-assured research outputs, in their goals and expectations, and in the services they provide and use. There are shared ambitions for significantly enhanced access, but no consensus on how best to achieve it.

Understanding the nature and implications of these changes, and the interrelationships between them, is thus of critical importance if we are to exploit the potential of new technologies and services to the full. The Research Information Network (RIN), the Joint Information Systems Committee (JISC), the Association of Learned and Professional Society Publishers (ALPSP), the Publishers Association (PA), the British Library (BL), Research Libraries UK (RLUK), the Society of College, National and University Libraries (SCONUL), SPARC Europe, Research Councils UK (RCUK), Universities UK (UUK), the Wellcome Trust and others have been working to this end. They are now seeking to establish a joint portfolio of work to underpin and facilitate transitions over the next few years.

The joint portfolio will focus intially on four projects, though more may follow:

- Transitions to e-only publication, which will investigate the barriers – from the perspectives of libraries, publishers and users – to moving to e-only publishing of scholarly journals, and ways in which those barriers might be overcome;

- Gaps in access, which will investigate the extent to which journal articles and other research outputs are available, or not, to different parts of the research and other communities which could make use of them; and to identify priorities in seeking to fill gaps in access, barriers to filling them, and actions that might be taken to that end;

- Dynamics of improving access to research papers, which will provide evidence for a better understand of the dynamics of the transitions needed to reach a selection of plausible end-points, and the costs, benefits, opportunities and risks that this entails. Transition is understood to relate to changes in practice, business models and organisational culture within the relevant constituencies, and any new entrants, over defined timeframes. The end-points, to be defined in advance of the project, will be associated with four broad models: open access journals (gold OA); open access repositories (green OA); extensions to licensing; and transactional solutions.The project will be founded on a comparative description of the transitions that (i) are taking place now, and (ii) would need to take place over the next five years, in order to reach each of the selected end-points. There will also be an analysis of the drivers and mechanisms underlying these transitions, and associated costs and benefits (both cash and non-cash).

- Futures  for scholarly communications, which will seek to develop a series of challenging scenarios for scholarly communications in ten years’ time, bearing in mind current trends and underlying drivers in user cultures, needs and expectations; and likely – and more speculative - developments in  technologies and services. Through the process of developing the scenarios we shall promote constructive dialogue between stakeholders, and seek to establish priorities for action.

The bodies listed above will work together on these projects with the aim of building a common understanding of the incentives, constraints, costs and benefits associated with the shared goals of widening access to research outputs; and of promoting the continuing development of a scholarly communications system that is sustainable, efficient and effective in meeting the needs and aspirations of the research community in the UK and globally.

Each body will also share information about other projects that they undertake related to those shared goals.